## Data
Workstream | Owner | Budget (€) | Actual Cost (€) | Forecast Cost (€) | Planned Progress % | Actual Progress % | Open Risks | Status | Budget Variance | Forecast Variance | Progress Variance
Requirements | Anna | 8000 | 7500 | 7800 | 100% | 100% | 0 | Green | 500 | 200 | 0%
Development | Mark | 30000 | 22000 | 32000 | 75% | 70% | 3 | Amber | 8000 | -2000 | -5%
Testing | Sarah | 12000 | 5000 | 11500 | 50% | 40% | 2 | Red | 7000 | 500 | -10%
Training | Lukas | 6000 | 1500 | 6500 | 30% | 20% | 1 | Amber | 4500 | -500 | -10%
Deployment | Emma | 9000 | 0 | 9000 | 10% | 0% | 1 | Green | 9000 | 0 | -10%

## Dashboard
KPI | Result | DIGITAL TRANSFORMATION PROJECT DASHBOARD
Total Budget | 65000 | Budget, Forecast & KPI Performance Overview
Actual Spend | 36000 | TOTAL BUDGET | Actual Spend | Forecast Cost | Project Progress | Open Risks
Forecast Cost | 66800 | 65000 | 36000 | 66800 | 46% | 7
Remaining Budget | 29000
Forecast Variance | -1800
Budget Utilization | 55.38% | Remaining Budget |  | Forecast Variance
Overall Progress | 46% | 29000 |  | -1800
Open Risks | 7
Management Insights | [6 empty] | RAG Status Summary
Development is forecast to exceed budget by €2,000. | [6 empty] | Workstream | Status | Reason
Testing is 10 percentage points behind planned progress | [6 empty] | Requirements | Green | Completed as planned
Overall project completion is 46%. | [6 empty] | Development | Amber | 5% behind plan and forecast over budget
The project is forecast to exceed the total budget by €1,800. | [6 empty] | Testing | Red | 10% behind planned progress
[7 empty] | Training | Amber | 10% behind plan and forecast over budget
[7 empty] | Deployment | Green | Not yet started; no current cost overrun

## Notes
Project Title
Digital Transformation Project Performance Dashboard
Objective
To create a simple project management dashboard for monitoring budget, actual spend, forecast cost, project progress, open risks, and overall project status.
Tools Used
Microsoft Excel, formulas, charts, conditional formatting, KPI cards, and RAG status reporting.
Key Metrics Tracked
Total budget
Actual spend
Forecast cost
Remaining budget
Forecast variance
Budget utilization
Overall progress
Open risks
Key Findings
Total project budget: €65,000
Forecast project cost: €66,800
Forecast overrun: €1,800
Overall progress: 46%
Development is forecast to exceed budget and is behind schedule
Testing is 10 percentage points behind planned progress
Dashboard Purpose
The dashboard provides management with a quick overview of project financial performance, schedule performance, risks, and areas requiring attention.
Note: This dashboard uses fictional project data and was created as a portfolio exercise.